## schedule
Task ID | Work Breakdown Structure |  |  |  |  | Planned Start | Planned Finish | Actual Start | Actual Finish | Workload （Plan｜Actual） |  | In Charge | Progress | (Mar-12th-18) | (Mar-19th-18) | (Mar-26th-18) | (Apr-2nd-18) | (Apr-9th-18) | (Apr-16th-18) | (Apr-23rd-18) | (Apr-30th-18) | (May-7th-18) | (May-14th-18) | (May-21st-18) | (May-28th-18) | (Jun-4th-18) | (Jun-11th-18) | (Jun-18th-18) | (Jun-25th-18) | (Jul-2nd-18) | (Jul-9th-18) | (Jul-16th-18) | (Jul-23rd-18) | (Jul-30th-18) | (Aug-6th-18) | (Aug-13th-18) | (Aug-20th-18)
id | lv1 | lv2 | lv3 | lv4 | lv5 | plannedStart | plannedFinish | actualStart | actualFinish | plannedWorkload | actualWorkload | responsiblity | progress
1 | Timing |  |  |  |  | 2018-03-08 | 2018-03-12 |  |  | 10 |  | Chris | 50%
2 | Maze Design Mockups |  |  |  |  | 2018-03-08 | 2018-03-12 |  |  |  |  | Erick | 100%
3 | User Instruction Draft |  |  |  |  | 2018-03-08 | 2018-03-14 |  |  |  |  | Erick & Chris | 0%
4 | Random |  |  |  |  | 2018-03-12 | 2018-03-19 |  |  |  |  | Chris | 0%
5 | Player |  |  |  |  | 2018-03-12 | 2018-03-19 |  |  |  |  | Erick | 100%
6 | Items |  |  |  |  | 2018-03-12 | 2018-03-26 |  |  |  |  | Chris | 0%
7 | Mouse Logic |  |  |  |  | 2018-03-19 | 2018-03-26 |  |  |  |  | Erick | 75%
8 | Player Contact |  |  |  |  | 2018-03-26 | 2018-03-28 |  |  |  |  | Chris | 0%
9 | AI Logic |  |  |  |  | 2018-03-26 | 2018-03-28 |  |  |  |  | Erick | 80%
11 | Logic Bugs |  |  |  |  | 2018-03-12 | 2018-03-28 |  |  |  |  | Erick & Chris | 0%
12 | Graphics Bugs |  |  |  |  | 2018-03-12 | 2018-03-28 |  |  |  |  | Erick & Chris | 0%
13 | Level Progression |  |  |  |  | 2018-03-12 | 2018-03-19 |  |  |  |  | Erick & Chris | 0%
14 | Clouding |  |  |  |  | 2018-03-21 | 2018-03-28 |  |  |  |  | Erick & Chris | 50%
15 | Asset Graphics |  |  |  |  | 2018-03-12 | 2018-03-28 |  |  |  |  | Erick & Chris | 0%
16 | Finalization |  |  |  |  | 2018-03-26 | 2018-03-28 |  |  |  |  | Erick & Chris | 0%

## holiday
2017-12-31 08:00 | Sample Holiday
Note on A1: When editing holidays, please set date only in the A column.